## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
Kordell |  | 2. Save to one team member's Google drive
Jurgen |  | 3. Share file with other team members
Elisabeth |  | 4. Edit First Names on this tab
George |  | 5. Add your team name to the name of this document
Peyton |  | 6. For each sprint, duplicate the sprint template and change the start date
DOCUMENT HISTORY
| 2017-09-20 | Created by Justin Sybrandt (http://sybrandt.com/post/google-slides-agile/)
| 2019-03-23 | Modified by Susanne Sherba for use in COMP 3381 (Software Engineering I)

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
| S0 | Drag card | As a student I want to be able to drag cards to their answers so that I can create matched sets |  | 1-high | Done
| S1 | Student Login | As a student, I want to be able to login and join a instance of the game so that I can interact with other students. |  | 1-high | Done
| S2 | Website access | As a teacher I want to be able to join the game with my students so that I can watch them play and see their thought process. |  | 1-high | Done
| S3 | See others' movements | As a student I want to see my teammates moving their cards in real time so that I know what matches they think are correct |  | 2-medium | Done
| S4 | Connect to an instance | As a student, I want to be able to connect an instance of a game so that I can interact with other students or by myself to practice my calculus skills. |  | 1-high | Done
| S6 | Make maches of 3 cards | As a student, I want to be able to match 3 cards together so that I can create a match set that is then removed from the cards I need to consider |  | 1-high | Done
| S7 | Leave the game | As a student I want to be able to leave the game after completion so I don't have to exit the site. |  | 3-low | In Progress
| S9 | Add Additional Cards | As a Teacher, I want to be able to add additional sets of cards to the game after initial publication so that I can expand my game and create new material |  | 3-low | Done | Note: This is very doable for a coder, as our code was designed to be easily reusable for new sets. This is not doable for an average user.
| S10 | Visibility of Matches | As a student, I want to be able to view my existing matches so that I can track my progress to completion. |  | 2-medium | Done
| S12 | Cards on/off table | As a student I want to be able to add and remove cards from the table so that I can see all my remaining options. |  | 1-high | Done
| S13 | Correct Answer Breakdown | As a Teacher, I want to be able to view the answers breakdown for every group so that I can see what groups understand the concepts. |  | 3-low | Done
| S14 | Group Matched Sets | As a student, I want to be able to separate matched sets from unmatched sets so that I know which cards still need attention |  | 2-medium | Done
| S15 | Unmatch a set | As a student, I want to be able to review matched sets and unmatch then do that if I made a mistake in creating a set it can be corrected |  | 2-medium | Done
| S16 | Exit a game | As a student, I want to be able to exit a game so that I can return to the main menu at any time |  | 2-medium | In Progress
| S17 | Zoom in on a card | As a student, I want to be able to zoom in on cards so that I can have a better understanding of the contents on the card |  | 3-low | Done
| S18 | See Cards | As a student, I want to be able to see cards with some kind of calculus information on them so I know what properties I'm trying to match |  | 1-high | Done
| S19 | Remaining cards | As a student, I want to be ablle to see all of the cards I have left to match so that I can see my remaining options |  | 2-medium | Done
| S20 | Choose a game | As a student, I want to be able to choose which game I want to play so that I can focus on the areas in which I need imporvement |  | 3-low | Done
| S21 | Remove matches from table | As a player, I want to be able to remove matched sets from the table so that my playing space isn't cluttered with cards I have already addressed. |  | 2-medium | In Progress

## Sprint Template (Make a copy!)
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | Brief description |  |  |  | To Do |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-03-30 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Start Date: | 2019-03-30 | Kordell | 0 | 0 | 0% | 2019-03-31 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Sprint Length | 14 | Jurgen | 0 | 0 | 0% | 2019-04-01 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Hours Per Day: | 0 | Elisabeth | 0 | 0 | 0% | 2019-04-02 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | George | 0 | 0 | 0% | 2019-04-03 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Peyton | 0 | 0 | 0% | 2019-04-04 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  |  | 0 | 0 | 0% | 2019-04-05 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-06 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Total: | 0 | 0 | 0% | 2019-04-07 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-08 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-09 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-10 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-11 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-12 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-13 | 0 | 0 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | Make a better login screen that shows current up and running servers | 3 | 4 | Elisabeth | Done | 2019-05-18 | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-05-17 | 0 | 0 | 73 | 73
S1 | Make a better login screen that shows current up and running servers | 3 | 4 | Jurgen | Done | 2019-05-18 | Start Date: | 2019-05-17 | Kordell | 12 | 12 | 100% | 2019-05-18 | 9 | 9 | 64 | 67.7857
S1 | Make a better login screen that shows current up and running servers | 3 | 4 | Peyton | Done | 2019-05-18 | Sprint Length | 14 | Jurgen | 16 | 16 | 100% | 2019-05-19 | 0 | 9 | 64 | 62.5714
S17 | Find a way to spawn and display cards that allows for ease of play | 2 | 2 | Kordell | Done | 2019-05-21 | Hours Per Day: | 5.2143 | Elisabeth | 15 | 15 | 100% | 2019-05-20 | 2 | 11 | 62 | 57.3571
S17 | Find a way to spawn and display cards that allows for ease of play | 2 | 2 | Peyton | Done | 2019-05-21 |  |  | George | 16 | 16 | 100% | 2019-05-21 | 7 | 18 | 55 | 52.1429
S20 | Create a transition screen that allows users to choose which game they want to play | 1 | 1 | Elisabeth | Done | 2019-05-21 |  |  | Peyton | 14 | 14 | 100% | 2019-05-22 | 2 | 20 | 53 | 46.9286
S0 | Finish parsing the cards into prefabs so they can be made into game sets | 2 | 2 | George | Done | 2019-05-21 |  |  |  | 0 | 0 | 0% | 2019-05-23 | 0 | 20 | 53 | 41.7143
S19 | Update button images so they match the cards they correspond to. | 4 | 4 | George | Done | 2019-05-26 | [6 empty] | 2019-05-24 | 1 | 21 | 52 | 36.5
S6 | Make a Card spawner | 2 | 2 | Kordell | Done | 2019-05-20 |  |  | Total: | 73 | 73 | 100% | 2019-05-25 | 0 | 21 | 52 | 31.2857
S6 | Implement Game logic | 4 | 4 | Jurgen | Done | 2019-05-28 | [6 empty] | 2019-05-26 | 14 | 35 | 38 | 26.0714
S10 | Come up with some storage place for cards that have been deemed a match to go | 1 | 1 | Elisabeth | Done | 2019-05-27 | [6 empty] | 2019-05-27 | 25 | 60 | 13 | 20.8571
S0 | Add all card prefabs and link them with their respective sprites. | 2 | 2 | George | Done | 2019-05-22 | [6 empty] | 2019-05-28 | 5 | 65 | 8 | 15.6429
S15 | UI and syncing the matches and general displays | 7 | 7 | Elisabeth | Done | 2019-05-26 | [6 empty] | 2019-05-29 | 7 | 72 | 1 | 10.4286
S15 | UI and syncing the matches and general displays | 7 | 11 | Kordell | Done | 2019-05-27 | [6 empty] | 2019-05-30 | 0 | 72 | 1 | 5.2143
S15 | UI and syncing the matches and general displays | 7 | 11 | Jurgen | Done | 2019-05-27 | [6 empty] | 2019-05-31 | 0 | 72 | 1 | 0
S15 | UI and syncing the matches and general displays | 7 | 11 | Peyton | Done | 2019-05-27 | [7 empty] | 1 | 73 |  | 0
S15 | UI and syncing the matches and general displays | 3 | 4 | George | Done | 2019-05-27 | [7 empty] | 1 | 65 |  | 0
S16 | Make an exit button and instructions | 1 | 1 | Elisabeth | Done | 2019-05-28 | [7 empty] | 1 | 66 |  | 0
S0 | Added photon views to all cards | 3 | 3 | George | Done | 2019-05-26 | [6 empty] | #REF! | 0 | 57 | #REF! | #REF!
S4 | Duplicate derivative scene 4x, debug resulting errors | 1 | 1 | George | Done | 2019-05-24 | [6 empty] | #REF! | 0 | 55 | #REF! | #REF!
ALL | Debugging Part 1 | 1 | 1 | Kordell | Done | 2019-05-29 | [6 empty] | #REF! | 0 | 55 | #REF! | #REF!
ALL | Debugging Part 1 | 2 | 2 | Jurgen | Done | 2019-05-29 | [6 empty] | #REF! | 0 | 54 | #REF! | #REF!
ALL | Debugging Part 1 | 2 | 2 | Peyton | Done | 2019-05-29 | [6 empty] | #REF! | 0 | 54 | #REF! | #REF!
ALL | Debugging Part 1 | 2 | 2 | Elisabeth | Done | 2019-05-29 | [6 empty] | #REF! | 0 | 40 | #REF! | #REF!
ALL | Debugging Part 1 | 1 | 1 | George | Done | [7 empty] | #REF! | 0 | 15 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 10 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 3 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 3 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 3 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 2 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 1 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 0 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 0 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 0 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 0 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 0 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 0 | #REF! | #REF!
[5 empty] | To Do | [7 empty] | #REF! | 0 | 0 | #REF! | #REF!
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 2
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S4* | Finish the test multiplayer game | 4 | 10 | Elisabeth | Done | 2019-05-13 | Sprint Number: | 2 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-05-03 | 0 | 0 | 25 | 25
S2 | Add a welcome page to the cs server site | 3 | 2:15 | Kordell | Done | 2019-05-10 | Start Date: | 2019-05-03 | Kordell | 3 | 3 | 100% | 2019-05-04 | 0 | 0 | 25 | 23.2143
S2 | Add a welcome page to the cs server site | 3 | 2:15 | Peyton | Done | 2019-05-10 | Sprint Length | 14 | Jurgen | 4 | 4 | 100% | 2019-05-05 | 0 | 0 | 25 | 21.4286
S2 | Push a Test unity project to the CS server | 1 | 1 | Peyton | Done | 2019-05-08 | Hours Per Day: | 1.7857 | Elisabeth | 4 | 4 | 100% | 2019-05-06 | 0 | 0 | 25 | 19.6429
S4* | Finish the test multiplayer game | 4 | 10 | Peyton | Done | 2019-05-13 |  |  | George | 6 | 6 | 100% | 2019-05-07 | 0 | 0 | 25 | 17.8571
S4* | Finish the test multiplayer game | 4 | 10 | Jurgen | Done | 2019-05-13 |  |  | Peyton | 8 | 8 | 100% | 2019-05-08 | 1 | 1 | 24 | 16.0714
S4* | Help debug server implementation | 3 | 3 | George | Done | 2019-05-13 |  |  |  | 0 | 0 | 0% | 2019-05-09 | 0 | 1 | 24 | 14.2857
S5 | Redesign main menu | 3 | 3 | George | Done | 2019-05-13 | [6 empty] | 2019-05-10 | 6 | 7 | 18 | 12.5
| * = Faan Tone Request. |  |  |  | To Do |  |  |  | Total: | 25 | 25 | 100% | 2019-05-11 | 0 | 7 | 18 | 10.7143
[5 empty] | To Do | [7 empty] | 2019-05-12 | 0 | 7 | 18 | 8.9286
[13 empty] | 2019-05-13 | 18 | 25 | 0 | 7.1429
[5 empty] | To Do | [7 empty] | 2019-05-14 | 0 | 25 | 0 | 5.3571
[5 empty] | To Do | [7 empty] | 2019-05-15 | 0 | 25 | 0 | 3.5714
[5 empty] | To Do | [7 empty] | 2019-05-16 | 0 | 25 | 0 | 1.7857
[5 empty] | To Do | [7 empty] | 2019-05-17 | 0 | 25 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 25 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 25 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 25 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 25 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 25 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 24 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 24 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 18 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 18 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 18 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S4 | Research Sockets and see how they would interact with a bare minimum unity project. Attempt to post on itch.io | 5 | 3 | Elisabeth | Done | 2019-04-20 | Sprint Number: | 1 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-04-19 | 3 | 3 | 26 | 29
S0 | Make a bare minimum unity project that allows for cards to be moved across the screen for the purposes of testing | 3 | 2 | Jurgen | Done | 2019-04-19 | Start Date: | 2019-04-19 | Kordell | 4 | 4 | 100% | 2019-04-20 | 5 | 8 | 21 | 26.9286
S4 | Make a scene in the untiy project for login and one for selecting the game to play | 3 | 2 | Peyton | Done | 2019-04-25 | Sprint Length | 14 | Jurgen | 7 | 7 | 100% | 2019-04-21 | 0 | 8 | 21 | 24.8571
S18 | Take the current game set of card and create some form of importable data into unity | 4 | 2 | Kordell | Done | 2019-05-01 | Hours Per Day: | 2.0714 | Elisabeth | 9 | 9 | 100% | 2019-04-22 | 0 | 8 | 21 | 22.7857
S4 | Talk to Andres about how to upload all of the pieces to the CS Server and what protocols need be followed for pushing changes. Then take that knowledge and try and push a unity project to the CS server | 3 | 2 | George | Done | 2019-04-27 |  |  | George | 3 | 3 | 100% | 2019-04-23 | 0 | 8 | 21 | 20.7143
S4 | NOTE: this will take more than 1 sprint. Figure out the Network Manager Multiplayer portion of Unity/Follow the tutorial for making a new multiplayer project | 4 | 4 | Elisabeth | Done | 2019-05-02 |  |  | Peyton | 6 | 6 | 100% | 2019-04-24 | 0 | 8 | 21 | 18.6429
S0 | Create playing card pre-fab | 2 | 1.5 | Jurgen | Done | 2019-04-30 |  |  |  | 0 | 0 | 0% | 2019-04-25 | 4 | 12 | 17 | 16.5714
| Consolidate unity projects and update git repo | 2 | 1 | Jurgen | Done | 2019-04-30 | [6 empty] | 2019-04-26 | 0 | 12 | 17 | 14.5
S4 | Connect to server and push documents | 2 | 2 | Peyton | Done | 2019-04-28 |  |  | Total: | 29 | 29 | 100% | 2019-04-27 | 3 | 15 | 14 | 12.4286
S4 | Combine the following scenes: card moved across screen, user login and server select | 1 | 1 | Peyton | Done | 2019-04-25 | [6 empty] | 2019-04-28 | 2 | 17 | 12 | 10.3571
[5 empty] | To Do | [7 empty] | 2019-04-29 | 0 | 17 | 12 | 8.2857
[5 empty] | To Do | [7 empty] | 2019-04-30 | 4 | 21 | 8 | 6.2143
[5 empty] | To Do | [7 empty] | 2019-05-01 | 4 | 25 | 4 | 4.1429
[5 empty] | To Do | [7 empty] | 2019-05-02 | 4 | 29 | 0 | 2.0714
[5 empty] | To Do | [7 empty] | 2019-05-03 | 0 | 29 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 26 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 21 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 21 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 21 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 21 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 21 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 17 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 17 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 14 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 12 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 12 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 8 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 4 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 0
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | Task 1 | 1 |  | Kordell | To Do |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-04-06 | 0 | 0 | 19 | 19
S1 | Task 2 | 3 |  | Jurgen | To Do |  | Start Date: | 2019-04-06 | Kordell | 1 | 0 | 0% | 2019-04-07 | 0 | 0 | 19 | 17.6429
S1 | Task 3 | 4 |  | Elisabeth | To Do |  | Sprint Length | 14 | Jurgen | 3 | 0 | 0% | 2019-04-08 | 0 | 0 | 19 | 16.2857
S1 | Task 4 | 5 |  | George | To Do |  | Hours Per Day: | 1.3571 | Elisabeth | 4 | 0 | 0% | 2019-04-09 | 0 | 0 | 19 | 14.9286
S1 | Task 5 | 6 |  | Peyton | To Do |  |  |  | George | 5 | 0 | 0% | 2019-04-10 | 0 | 0 | 19 | 13.5714
[5 empty] | To Do |  |  |  | Peyton | 6 | 0 | 0% | 2019-04-11 | 0 | 0 | 19 | 12.2143
[5 empty] | To Do |  |  |  |  | 0 | 0 | 0% | 2019-04-12 | 0 | 0 | 19 | 10.8571
[5 empty] | To Do | [7 empty] | 2019-04-13 | 0 | 0 | 19 | 9.5
[5 empty] | To Do |  |  |  | Total: | 19 | 0 | 0% | 2019-04-14 | 0 | 0 | 19 | 8.1429
[5 empty] | To Do | [7 empty] | 2019-04-15 | 0 | 0 | 19 | 6.7857
[5 empty] | To Do | [7 empty] | 2019-04-16 | 0 | 0 | 19 | 5.4286
[5 empty] | To Do | [7 empty] | 2019-04-17 | 0 | 0 | 19 | 4.0714
[5 empty] | To Do | [7 empty] | 2019-04-18 | 0 | 0 | 19 | 2.7143
[5 empty] | To Do | [7 empty] | 2019-04-19 | 0 | 0 | 19 | 1.3571
[5 empty] | To Do | [7 empty] | 2019-04-20 | 0 | 0 | 19 | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")